## Gantt Chart
GANTT CHART - E90 Project
PROJECT TITLE |  | E90 Project - Shell Eco-Marathon Vehicle |  |  |  |  | SCHOOL NAME | [6 empty] | Swarthmore College
NAMES |  | Justin Chai and Ben Horvat |  |  |  |  | DATE | [6 empty] | 2023-11-08
[37 empty] | RETURN TO CAMPUS | [34 empty] | SPRING BREAK WEEK | [38 empty] | END OF CLASSES
[7 empty] | DATE: 12/11/2023 | [14 empty] | Start of 2024 | [14 empty] | DATE: 1/22/2023 | [14 empty] | DATE: 2/12/2023 | [14 empty] | DATE: 3/4/2023 | [14 empty] | DATE: 3/25/2023 | [14 empty] | DATE: 4/15/2023 | [13 empty] | DATE: 5/3/2024
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | PHASE ONE | [29 empty] | PHASE TWO | [29 empty] | PHASE THREE | [9 empty] | PHASE FOUR/FIVE
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12 |  |  |  |  | WEEK 13 |  |  |  |  | WEEK 14 |  |  |  |  | WEEK 15 |  |  |  |  | WEEK 16 |  |  |  |  | WEEK 17 |  |  |  |  | WEEK 18 |  |  |  |  | WEEK 19 |  |  |  |  | WEEK 20 |  |  |  |  | WEEK 21 |  |  |  |  | WEEK 22 |  |  |  |  | WEEK 23 |  |  |  |  | WEEK 24
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Design
1.1 | Research - Best Methods | BH+JC |  |  | 5 | 0% | bar: WEEK 1 M to WEEK 1 F
1.2 | Overall System Selection |  |  |  | 5 | 0% | bar: WEEK 3 M to WEEK 3 F
1.3 | Steering + Brake System Selection | BH+JC |  |  | 5 | 0%
1.4 | Chasis Design - CAD | BH |  |  | 10 | 0% | bar: WEEK 4 M to WEEK 5 F
1.5 | Suspension + Brake Calcs | JC+BH |  |  | 5 | 0% | bar: WEEK 6 M to WEEK 6 F
1.6 | Electrical + Fluids Management Plans | JC |  |  | 5 | 0% | bar: WEEK 5 W to WEEK 6 T
2 | Frame Construction
2.1 | Welding Training |  |  |  | 5 | 0% | bar: WEEK 7 M to WEEK 7 F
2.2 | Material Aquisition |  |  |  | 5 | 0% | bar: WEEK 7 M to WEEK 7 F
2.3 | Construction |  |  |  | 20 | 0% | bar: WEEK 8 M to WEEK 11 F
2.4 | Finishing Touches |  |  |  | 3 | 0% | bar: WEEK 12 M to WEEK 12 F
3 | Suspension + Wheel Construction
3.1 | Material Requisition/Aquisition |  |  |  | 5 | 0% | bar: WEEK 12 M to WEEK 12 F
3.2 | Frame Mounting |  |  |  | 2 | 0% | bar: WEEK 13 M to WEEK 13 T
3.2.1 | Adjustments + Testing |  |  |  | 8 | 0% | bar: WEEK 13 W to WEEK 14 F
4 | Electrical
4.1 | Frame Modifications |  |  |  | 2 | 0% | bar: WEEK 15 M to WEEK 15 T
4.2 | Install |  |  |  | 6 | 0% | bar: WEEK 17 M to WEEK 18 M
4.3 | Adjustments + Testing |  |  |  | 4 | 0% | bar: WEEK 18 T to WEEK 18 F
4.4 | Critical Safety Systems (E-Stops) |  |  |  | 4 | 0% | bar: WEEK 19 M to WEEK 19 R
4.5 | Hydrogen Fuel Cell + Tank Hookup |  |  |  | 4 | 0% | bar: WEEK 23 M to WEEK 23 R
5 | Brakes
5.1 | Frame Modifications |  |  |  | 2 | 0% | bar: WEEK 15 W to WEEK 15 R
5.2 | Install |  |  |  | 2 | 0% | bar: WEEK 15 F to WEEK 16 M
5.3 | Testing + Adjustments |  |  |  | 6 | 0% | bar: WEEK 21 M to WEEK 21 F
6 | Testing
6.1 | Hydrogen Fuel Cell Test |  |  |  | 5 | 0%
6.2 | Functional Test |  |  |  | 3 | 0%
6.3 |  |  |  |  | 0 | 0% | bar: WEEK 23 F to WEEK 24 R
MISC | E90 Items
A.1 | Project Proposal Due |  |  | 2024-12-15 | 1 | 0% | bar: WEEK 1 M to WEEK 1 F
A.2 | Practice Presentation Due |  |  | 2024-03-29 | 5 | 0% | bar: WEEK 16 M to WEEK 16 F
A.3 | Draft Report |  |  | 2024-04-26 | 5 | 0%
A.4 | Final Report |  |  | 2024-05-10 | 5 | 0% | bar: WEEK 22 M to WEEK 22 F
A.5 | Parents Dinner |  |  | 2024-05-24 | 1 | 0% | bar: WEEK 24 F